## Sheet1
Name: | P. Rahul Sai Vishnu
Id: | T0004
Effort Estimation from 07-05-2018 To 11-05-2018
Date |  | Task Assigned | Estimated Time | Actual Time | Task Status
2018-05-07 |  | AIM Seva Send Notification Via Email And SMS | 9 hrs | 9 hrs | Completed
2018-05-08 |  | AIM Seva Send Notification by Binding the Donor_id | 9 hrs | 9 hrs | Completed
2018-05-09 |  | Update All Tables in the Dashboard and Notify | 9 hrs | 9 hrs | Completed
2018-05-10 |  | Mail Module/ Identifying Components for Nicholas | 9hrs | 9 hrs | N/ Y
2018-05-11 |  | Mail Module With Various Functionality | 9 hrs | Working | Working
Mail Time : 11:30 AM