## Sheet1
Name : | N.Pavithra
ID : | T0002
2018-05-07
Task For the Day |  | Estimated Time | Time Taken | Status
Working in some of the bugs for AIM FOR SEVA |  | 3 hours | 4 hours | Completed
Analysing about MongoDB basics |  | 1 hour | 2 hours | Completed
Implementing the first set of Queries in MongoDB |  | 4 hours | 6 hours | Completed
2018-05-08
Task For the Day
Impleting the next set of Queries |  | 3 hours | 4 hours | Completed
CRUD Operations in MongoDB |  | 1 hour | 1 hour | Completed
Retreiving Data from SQL database |  | 1 hour | 1 hour | Completed
2018-05-09
Task For the Day
Implementing the next set of Queries |  | Half day | Half day | Completed
Nicholas Kick-off Meeting |  | 2 hours | 2 hours
Testing AIM For Seva |  | 1 hour | 1 hour | Completed
Preparing Query Document for Nicholas along with Adithya |  | 1 hour | 1 hour | Completed
2018-05-10
Task For the Day
Requirements Gathering of Boonbox |  | 5 hours | 5 hours | Completed
Preparing Document for the Requirements |  | 2 hours | 2 hours | Completed
MongoDB Queries(Nested Documents) |  | 2 hours | 2 hours | Completed
2018-05-11
Task For the Day
Boonbox Meeting Cancelled
Analyzing about Typescript |  | 6 hours | 6 hours | Pending
Bug Fixing for AIM For Seva |  | 4 hours | 4 hours | Completed
2018-05-12
Task For the Day
Joins in MongoDB |  | 4 hours | 3 hours | Completed
Fixing Bugs in AIM For Seva |  | 4 hours | 5 hours | Completed
2018-05-14
Task For the Day
Filters in MongoDB |  | 3 hours
Creating Branches in GItHub Repository |  | 1 hour
Typescript Example Programs |  | Half Day