## Sheet1
Name: | P. Rahul Sai Vishnu
Id: | T0004
Effort Estimation from 07-05-2018 To 11-05-2018
Date |  | Task Assigned | Estimated Time | Actual Time | Task Status
2018-05-07 |  | AIM Seva Send Notification Via Email And SMS | 9 hrs | 9 hrs | Completed
2018-05-08 |  | AIM Seva Send Notification by Binding the Donor_id | 9 hrs | 9 hrs | Completed
2018-05-09 |  | Update All Tables in the Dashboard and Notify | 9 hrs | 9 hrs | Completed
2018-05-10 |  | Mail Module/ Identifying Components for Nicholas | 9hrs | 9 hrs | N/ Y
2018-05-11 |  | Mail Module With Various Functionality | 9 hrs | 9 hrs | Completed
2018-05-12 |  | Session retained after logout | 2 hrs | 1 hrs | Completed
|  | Screen Must Not Change As Per The URL change (AIM SEVA) | 2 hrs | 2 hrs | Completed
|  | Mail Module Sending mail after some time if mail is not sent | 2 hrs | 2 hrs | Completed
|  | Mail Module With Various Functionality | 3 hrs | 3 hrs | Completed
2018-05-14 |  | AIM SEVA Updates on Login Screen session | 5 hrs | 5 hrs | Completed
|  | Mail Module Changes and Identifying Components of Nicholas | 4 hrs | 4 hrs | Completed
2018-05-15 |  | AIM SEVA updates on Custom Validation For all Screens | 2 hrs | 2 hrs | Working